Example Reading Rampage Planning Calendar 2020 - Doncaster

| Reading Rampage Doncaster | Suggested Activities/Planning | Resources/Links | Key People | Subjects Involved |
| --- | --- | --- | --- | --- |
| 3rd – 7th February | Use Launch PPT in Assembly/ English Lessons to promote Reading Rampage (RR) Use posters to advertise beginning of project Announce to staff your ideas- all about Reading Rampage If running as an enrichment activity, begin sign up and book lending organisation Add promotional info to electronic signage Share photos/Tweet about your school launch | Launch PPT* Posters* Sign-up sheet Launch videos* | RR co-ordinator LRC/librarian Eng Dept | All staff to endorse RR Y7 and 8 Tutors to promote English Dept. to help launch |
| 10th – 14th February | Continue sign up and promote RR Complete pre- project survey online Gather reading data if using to measure reading improvements Check in with participating students Set up book groups and Y10 leads – decide which lunch time to use and organise schedule Discuss and plan with departments who will champion and promote each book Begin to circulate books/read books on rotation Announce your Book of the Week (#1) – use form time/English/assembly and announce linked department Set half term reading target Create book signage for chosen book (#1) Hand out A5 leaflets and bookmarks Start reading!! | Resource pack* Audio clip book taster* Reading surveys* Reading tests Resource pack* – link to your chosen book #1 Word searches* Audio clip book taster* Introducing the authors resource* Keeping A5 leaflets and bookmarks* | Link subject/dept Year 10 buddies | All staff to endorse RR Y7 and 8 Tutors to promote English Dept. to Link subject dept help launch |
| Half-term Break (17th – 21st Feb) – half term reading target for students |
| 24th-28th February | Announce your Book of the Week (#2 - #7)- – use form time/English/assembly and announce linked department Promote and tweet weekly challenges Check in with participating students Book Group Meetings (Meeting 1 – establish ground rules and routines – use book prompts booklet – students will have read different books so far so link those who have read same book together , give others the book of the week to discuss first impressions.) Create book signage each week (weeks 2 – 7) Create an activity linked to book or make linked resources available to students Thursday 5th March is World Book Day – link RR to your in-school activities Collect interim impact data. Numbers? Books read? Attitude and commitment? Promote again before holiday reading time | Resource pack* – link to your chosen book #2 to #7 Word searches* Audio clip book taster* Introducing the authors resource* | RR leads and book group buddies | All staff to endorse RR Y7 and 8 Tutors to promote WBD and RR |
| 2nd – 6th March |  |  |  |  |
| 9th – 13th March |  |  |  |  |
| 16th – 20th March |  |  |  |  |
| 23rd – 27th March |  |  |  |  |
| 30th – 3rd April |  |  |  |  |
| Term Break (6th - 17th April) – Easter reading challenge/target |
| 20th – 24th April | Announce your Book of the Week (#8 - #12)- – use form time/English/assembly and announce linked department Promote and tweet weekly challenges Check in with participating students Book Group Meetings Create book signage each week (weeks 8 - 12) Create an activity linked to book or make linked resources available to students Bank Holiday – Friday 8th May | Resource pack* – link to your chosen book #8 to #12 Word searches* Audio clip book taster* Introducing the authors resource* | RR leads and book group buddies | All staff to endorse RR Y7 and 8 Tutors to promote |
| 27th Apr – 1st May |  |  |  |  |
| 4th– 8th May |  |  |  |  |
| 11th – 15thMay |  |  |  |  |
| 18th - 22ndMay |  |  |  |  |
|  | Half-term Break (25th – 29th May) |
| 1st – 5th June | Announce your Book of the Week (#13-15)- – use form time/English/assembly and announce linked department Promote and tweet weekly challenges Check in with participating students Book Group Meetings Create book signage each week (weeks 13 -15) | Resource pack* – link to your chosen book #13 to #15 Word searches* Audio clip book taster* Introducing the authors resource* | RR leads and book group buddies |  |
| 8th – 12th June |  |  |  |  |
| 15th – 19th June |  |  |  |  |
| 22nd - 26th June | Use these weeks to enable students to catch up with the reading of books available and complete any tasks or in school competitions you have set Discuss final votes with students - remind students of judging criteria Collate borrowing figures to identify most borrowed book Encourage book returns Collect any creative challenges and activities to submit Begin to select Student award nominations, votes, student comments & creative and collect these ready for submission Data collection on numbers and book borrowing Inform SDSA of student winner and provide statement of how and why this student was chosen Decide which students are to attend the awards Send out permission letters, organise transport |  |  |  |
| 29th June - 3rd July | Celebrate in school – successes of the project - key students Complete Post Project survey with students online (hard copies also available) Reading test (if applicable) Report impact to SLT | Post project survey* Reading tests |  |  |
| W/C – 6th July | Attend Awards Event and CELEBRATE! | Risk assessments visit info | Mini bus driver and staff |  |

Resources/links *supplied by the Reading Rampage Team via https://readingrampage.org.uk/doncaster/